## task list
11/8 - 18/8 |  | 19/8 - 25/8 |  | 25/8 - 1/9 |  | 1/9 - 8/9 |  | 8/9 - 15/9 |  | 15/9 - 22/9 |  | 22/9 - 29/9 |  | 29/9 - 06/10 |  | 06/10 - 13/10 |  | 13/10 - 20/10 |  | 20/10 - 27/10 |  | 27/10 - 03/11 |  | 03/10 - 10/11 |  | 03/10 - 10/11 |  | 17/11 - 24/11 |  | 24/11 - 01/12 |  | 24/11 - 01/12 |  | 15/12 - 22/12 |  | 22/12 - 29/12 |  | 29/12 - 05/01 |  | 12/01 - 19/01 |  | 26/01 - 30/01 |  | 30/01 - 09/02 |  | 23/02-02/03 |  | 02/03-09/03 |  | 09/03-16/03 |  | 16/03-23/03 |  | 30/03-06/04 |  | 20/04-26/04 |  | 09/14-09/21 |  |  | 09/21-09/28
this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | planned for nxt week | this week | Status | planned for nxt week | this week | Status | planned for nxt week
Issue of TCU1 | Q1 to be run with scoreboard | Changes made in the files which were bringing error in some test cases | Q2 debugging and highlighting the issues to the dependencies again. | The BIMC and CATS enable were causing redirect issue, the issue was resolved by programming the field 'RCISH' of BIMC master port mode to '0'
Q2 test run | Q2 Debbuging | Q2 debbuging in progress
|  |  |  | Tests are run with commenting tcu1 master for checking whether it is the particular master which is responsible for causing error of timeout as the same error is seen in many of the test cases |  | The arlock was forced in the forces.do file for the masters tcu0 and tcu1 as the value was x' which made the aexclusive signal x' and thus causing the opcode decode problem for the noc. COMPLETED
|  |  |  | Exclusive tests have been added to the test list from bagheera |  | DONE
|  |  |  | Clock gating tests have been added to the list of cg testlist |  | 1 test case is failing, unable to gate the clock of tcu_s at pcnoc, programmed the smmu_cfg_cbcr registered as suggested by Karthik, but still failing PENDING CARRY FORWARD(1) | >>(1) | The clock to the slave was forced, so removed the force and after re run test PASS
[5 empty] | Baseline to be released | Released baseline for bus_integration:kichi_verif_bus_integration_v01 COMPLETED
[5 empty] | Functional coverage is to be generated | Tests were run and the failure of the two test cases is to be checked along with the test cases of redirect and memory reserved slave PENDING CARRY FORWARD(2) |  | The tests were re run as the bin for slave l2_cache got generated. | The functional coverage will be generated |  |  | The coverage of mss_q6_m for write inc , read inc, size 16 bit for slave cnoc_mpm,cnoc_rpm,cnoc_rbcpr is remaining, the apss_m -write wrap not covered |  | Write wrap for the apss_m is not covered, the test was run for covering the above, the coverage for all other master is made 100% |  | COMPLETED
[6 empty] | Tests case with l2_cache_enable was run after making changes to generate the wid PENDING CARRY FORWARD(3) | >>(3) | Pending |  | The changes regarding the slave monitor was required as the slave was of 128 bit , tests are passed COMPLETED
[6 empty] | 1 test case is failing, apss_m and ocimem_slave(excl_axi_128_apss) PENDING CARRY FORWARD (4) | >>(4) | Discussion was attended regarding the exclusive access, the test is to be seen for failure | To check the test failure | The address of the read ending with '8' was being converted to '0' at the time of write, the register 'OCI_MEM_GEN_CTRL' was programmed for exclusive monitor 128 granularity enable COMPLETED
|  |  |  | The scoreboard was updated with the address range of the slaves in the mst_slv_cfg_include file |  | DONE
[5 empty] | The Scoreboard tests run . | The scoreboard run is giving pending transfer error, in some cases it was due to different pid, the pid's has been changed. PENDING CARRY FORWARD TO NEXT WEEK (5) |  | The scoreboard for q1 was run for clearing the q1 tests with the scoreboard, changes were made for the slave address in mst_slave_cnfg_inc file. |  | The scoreboard for q1 has five error in xpu-cfg slaves , one in usb2_phy_cfg and one in security slave |  | The usb2_phy_cfg , pid bid was not be checked for the slave , so it was pushed to no_pid_bid_check(COMPLETED)
The reserved slave tests were run for checking the failure or incompleteness, the 2 tests were passed, and 2 were fail-lpass_lpm(reserved 6) and pronto_cmem_reserved
[8 empty] | Mail was sent to get the reserved address space for the respective slaves(To Sachin Bankar) | [5 empty] | The awid , wid mismatch for the gmem slave was the error for the test , the hvl top had only 4 bit as the wid due to which the range was not being covered as chip core top has 5 bit as Awid and wid(COMPLETED)
[8 empty] | Mail was sent to pavan kumar for verifying the mid's for the masters | [5 empty] | The test for apss_m is seen hanging as the transaction is not intiated by the transactor, the same is seen for the concur test with pronto slave, new vip version is used and test is run |  | The test were run with the new vip and the issue of missed transaction is not seen in the new version run.COMPLETED
[8 empty] | In redirect test cases, some of the address are being redirect to the intended slave but some of the addresses are being redirect to the snoc, the redirection problem is happening because of mss_selfauth.To be check, for now it is forced and test were run(Carry forward to next week) |  | The monitor at the slave end was of 64 bit due to which read write data mismatch error was coming, the monitor was changed to 128 bit and the mss self auth in the sequence for redirect test cases were made zero the tests were passed. COMPLETED
[8 empty] | Q3 test were run , 9 of the test were inconclusive(due to license) and the 2 test were failing, failing test cases are of security |  | Exclusions were made for excluding the bins to be covered in coverage, the coverage for tcu master(98.33%), mss_q6(96.53%) and apss(19.58%) is to be covered, the coverage for other master is 100% after applying the exclusion for boot rom, pronto, msg ram | The coverage for the masters is to be merged and cover |  |  |  |  | The deadlock test cases were run |  | PENDING | [11 empty] | After rebasing to kichi_v1.0_p2q1r13_verif_v1.52, the Simul error came, the test failed with read write data mismatch | To check the failure and clean the failures seen | Communicated the problem of ddr driver, and got the appt. changes for ddr driver file and memory instansiation, the changes worked and test were passed |  | Rebase to the dcd wrapper baseline for eldarion dcd. |  | Seen the first test case of dcd. |  | Testlist for system_noc_dcd.tl(functional test list) was changed for only mnoc masters. |  | Compilation issue for standalone test- changed the assert_pc_noc_dcd_checker_bind.sv file (compilation passed) | dcd for mclaren pcnoc | Sanity and functional test for both snoc and pcnoc are passed, The view names for both are: For snoc: c_jagtar_mclaren_system_noc_dcd_1.0 For pcnoc: c_jagtar_mclaren_pc_noc_1.0_1 | Test bench for noc needs to be generated | New stream for wifi noc, snoc eldarion, and shared view was made. | Test bench for noc needs to be generated | Filed a CR for ‘qhm_qdss_bam’. | Testplan and review closed: Wednesday | Reviewed the test plan for APB provided by iqbal |  | Addition to the test plan for APB with the information about checks and cover points coverage missing in the vip | Q1 review for lykan | Q1 review for lykan, mailed the results. | Coverage number publish after running all anvu tests. | Ran the anvu test and protocol coverage test for covering the min,mid,and max size of address, distributed idle state by the master with 200 reseed. | Publish the report of the exclusions needed to be made, and ask for the covergroups addition to the vip(from nitin)-Monday | Fatal error while extending the “user_apb_protocolCoverage” sequences from “anvu_apb_sequence” resolved | Initiator sending out of range address test (in progress) | Studied AHB and AXI | Done | .xls of ferro_lite received from Mansi. | To generate environment using .xls by Mansi | There were some login issues while the script run and solved it later.
[11 empty] | Q3 to be started | PENDING |  |  |  | COMPLETED
[12 empty] | The problem regarding the null object access halted the process, the new libs were not being created due to which the tests were getting the null object access error | COMPLETED
[12 empty] | The new rtl release has no interface ports for l2 cache slave, and the clock for the tcu master has been changed, the changes were made in the environment files | COMPLETED
The redirect test cases have been removed from the test list as the bimc is giving error for the redirect test cases
The tcu clock has been changed twice in a week , the changes were delivered to the bus integration baseline
The define for the scoreboard was added to the sequence, the problem of pending transfer was there in scbd tests due to change in the addresses
[14 empty] | The changes were made in the hvl top for checking the 11 bit of apss_m |  | COMPLETED
[16 empty] | The reserved slave test case of lpass reserved and pronto were seen with the issue of posted write, the test were run with the non posted write test arg for making hmemtype 'zero' the test case for lpass reserved passed |  | COMPLETED |  | Functional coverage meeting
[17 empty] | Toggle coverage to be done | The toggle coverage for the new rtl release was generated and the signals are to be checked for toggling | The toggle coverage for the snoc and pcnoc is to be completed | Exclusion for the pcnoc and snoc were made and need to get reviewed | Pending | [8 empty] | The oxili0_ahb test and gfx tcu test internal bridge clock issue were seen and the changes were made but the test still fails, need to get the correct fix | Toggle coverage dependency to be closed | The hsel at the bridge was found to be low, the particular hsel was forced to 1 in bus intg forces file and then the clk was issue was resolved and the transaction started reaching to slave, the test is passed |  | Compilation issue related to pkg not found was seen and resolved |  | Changed the checker and test bench file for snoc and mnoc top modules. |  | Standalone test, sanity test and functional test were given run for mnoc top(few incomplete test because of license checkout), ran the tests again(passed) |  | The baseline of noc for pc noc was being overridden by the earlier baseline(issue) | dcd for mclaren snoc | Changed the chip_bus_intg_mmms_func_def.sv for eladarion with `ifdef, | HLVR for the new noc is to be prepared | Steps were implemented for new noc verif environment needs (perforce environment) |  | Made HLVR for lykan noc | Testplan for all the testcases written for coverage, test, corner case functionality | Added the check/coverage points to the APB test plan and scheduled meeting to review the added points |  | Had a short review meet with iqbal about the added columns and correspondingly got the responses added by the vip team | Need to discuss about the work related to get 100% coverage and to re check the tasks | Adrastea noc APB initiator unaligned address ticket. Ticket for apb verification on qitc.bugs | identifying all the holes in coverage and the sequence required. getting single sequence reviewed with nitin writting single sequence for covering the holes. | Analysis of coverage report generated by running all the anvu test, the cover groups which are not covered are the part of exclusion group, (need to get reviewed once) | intermediate and final review of the sequences for coverage(by Thursday, to be sent in mail to nitin as a status update) | Changes in exclusion generating script for APB, first cut exclusion got reviewed (completed) | Discussion for master monitor wait zero bin hit(dump and details have been sent to nitin) | Generating environment of Ferro_lite( from Sratch) | Done
[18 empty] | The write wrap for the apss master was checked at the slave end, the test failure to be checked for data mismatch |  | wrap write for q1 data mismatch | Pending | Wrap write for q1 COMPLETED
[18 empty] | The pnoc pdm slave , config signal(hburst) mismatch was tracked and the changes were made to disable the hburst check |  | Apss axi master jira- |  | Kichi arg i.d. sheet fill
[18 empty] | A CR for qdss cfg reserved slave was filed and the test related info and result was answered in the mail chain |  |  |  |  | scoreboard test failure for q3 need to be checked and corrected | Corrected the failure of scoreboard for q3 test cases regarding apss 11 bit correction in hvl top,address not matching for pdm,so connected address bits from noc to the slave | Pending one test to pass for gfx tcu | gfx tcu with oxili ahb test is failing, the test case is being checked with 'smmu ahb access test' by oxili team. |  | The problem of internal clock was discussed with the security block people for oxili_ahb and gfx tcu slave, change has been provided by them in hvl_top_xpu_vdimt for clk enable, ran the test (fail) |  | Check list for llvr filled |  | The llvr for the project was presented and the toggle coverage report was shared to the noc designer for review of exclusions. |  | Generated the dcd test environment for eldarion after making new stream | The test environment for dcd now to be generated using single dcd wrappper top module from the previous baseline | The presentation for dual dcd changes was attended |  | Environment for mnoc dcd top module was generated |  | Due to overriding of the component various files were not there in the env. of dcd, resulting failure of standalone test,mailed the issue to scm.help | multi master multi slave test case clean | Ran 20 test cases, 9 passed, 11 fail (dec. error from bimc_slave).*(To run tests again after making changes) |  | Mailed vishal about the new gen_noc_tb requirement |  | Read qsb-qhb test plan and made apb test plan(need to get reviewed) | Testplan for all the testcases written for coverage, test, corner case observation port | Macros document received from vijay, seen the ppt and the use of Macros for the environment |  | Had a short discussin on meeting about the tickets for Adraste.noc | 1. basic sequence. 2. error sequence. 3. latency 4. performance 5. power 6. observation 7. interrupt 8. timeout | Made addition to the test plan for the coverage point sequences needed | writing basic sequence with weight as argument for different coverage hit. | Meeting with Nitin regarding the test case failure | Feero baseline is to be pick for making new stream and view for bus intg. | Held a session with aadil for VIP related issues pending—“Prdata”,”psel_range_max”,”configuring covergroup for change in address range”. | Covering ‘x’ or ‘z’ on signals given in test plan(hrdata and other In progress) | Complilation and test run using VCS | Cleaned the Compilation. Q1 tests are failing as Scoreboard is not showing the write transaction of mss_q6_m. |  |  | Studing each and every step of environment building process. In Progress.
[22 empty] | To cover pcnoc q2_h, such as hrdata, hwdata, the q3 tests were run with removing write not allowed test arg |  | Qdss cfg reserved timeout programming was used and the interrupt generation by the timeout was checked , the test is now failing initially it was hang |  |  |  | The bimc error test was made for bimc error response toggle coverage |  |  |  | The populate.sv file was regenerated for running deadlock test cases, the test cases got passed. | Get info on the work related to this, and do the required work | Done the web ex session with basil for apss 11 beat write and read transaction, with hang read transaction, uvm_info was added for start of read as suggested by basil, the test was run with changes. |  | The changes to the file of dual dcd was done with soumit |  |  | Scoreboard checking of ddr for the eldarion is to enabled | Made new stream for pcnoc dcd and re generated the environment | Check for qsb axi 64 bit transaction converted to 128 bit aligned transactions in scoreboard | Ran the multi master multi slave test cases for eldarion 20 run,16 passed,3 fail,1 incomplete |  | The xactor environment for noc was seen in the files generated by flex noc environment |  | Meeting QSB-AHB test plan checks and APB test plan points. | Testplan for all the testcases written for coverage, test, corner case performance/latency | Read the tickets related to Adrastea NOC (#AXI 3.0-Discovery VIP, vishal needs Nsys For it,#Htrans does not change to Idle in second cycle of AHB Error Response,#Wlan ordering Requirement) | To discuss the tickets related to Adrastea.NOC | Lykan NOC connectivity issue was seen for qxm_sdc1 | Test bench for Adrastea noc to be received form Nitin | Provided changes to resolve randomization failure in mclaren for qos test. | intermediate and final review of the sequences for coverage. | Filed a bug zila related to fatal error |  | Changes in test t_slverr.sv for APB,the test was getting hanged, changes relate dto configuration data base for slave sequence were made (completed) | Default pslverr =1 and pready =1
[20 empty] | Apss axi master jira- | Pending | Basil wants to see the sequence for the case |  | Q2_h for the slave such as tcu,Qhm_bimc_dehr,Hrdata for sdc1,sdc2 slave,were covered for the toggle coverage |  |  |  | Axi 32 test were added to make the transactions from dap master to the slaves on pcnoc |  |  |  | Mailed the coverage signals to be covered by security team and qdss team |  | The test were run with master ‘vfe’ and 2 more master, the issue of hang is not seen now, the test is failing now for timeout |  | Regression run test were getting incomplete, the switch for elab done for regression was added and the qvmr version was changed |  |  |  | Ran the test of multi master multi slave with changing timeout for qsb axi slave. |  | Following coverage bins for pcnoc dcd needed to be get reviewed: GEN_XM_XFER_CNT-66.66%,GEN_QHM_XFER_CNT-88.88%,GEN_XM_COVER-50%,GEN_QHM_COVER-88.88% |  | The coverage_lock file was generated for pcnoc dcd, the .cov file was generated, but the coverage still needs to be checked. |  | Setting env. and regression run explained to Anurag | Testplan for all the testcases written for coverage, test, corner case power | mclaren pc_noc baseline : mclaren_pc_noc_1.0_p3q2r2 , view name: c_jagtar_mclaren_pc_noc_3.0 mclaren_snoc baseline : mclaren_system_noc_1.0_p3q1r6; view name:c_jagtar_mclaren_system_noc_3.1 Gen noc tb was run after making new stream and view for both the mclaren noc. | Test bench for Adrastea noc to be received form Nitin | Reviewed the Toggle coverage for clock gating of Mclaren, 1. usb_phy_cfg 2. pcie_cfg_ahb 3. qhs8_qpic_cfg As the slvrdy for these slaves is 50% toggled with (1 to 0) not covered in Toggle coverage.(Test were added by Anuj) |  | Attended meeting for APB and jacal test bench bring up. Attended meeting for uvm_reg flow. |  | Mailed synopsys person Aadil about the pending issue of protocol check coverage compilation issue, webex session with him. |  | Ran the test without protocol coverage test and other with protocol coverage test for showing the report in meeting | delay insertion with pready low for covering bin related to wait 0-31,32-63,64-127,128.. And so on. | [5 empty] | New coverage bins – delta from previous project - part of check list
[24 empty] | Test regrading the q1 and q2 were re run to provide the clean status of all q2 test with webstat report but 2 test were found failing, need to check them for failure | Pending | multi pronto cmem slave test case were seen for timeout issue and the total transaction were checked in dump | [5 empty] | Rebased and got compile error for file missing. |  | The sequence for concur test cases of q2 was seen with Soumit. |  | Created two new streams under eldarion snoc for dcd dual and dcd mnoc |  |  |  | Rebase to the dcd wrapper baseline caused conflicts in baseline config., had to rebase to new baseline. |  | Tests for the qdss dap and rpm_m2 master were not there in the test list so the coverage related to both the master was not hit, so added the tests to the list and ran the tests |  | Test plan for eos_pmu_noc_block_verif was read |  | Meeting for APB test plan review attended | Testplan for all the testcases written for Error scenarios |  | VIP functional coverage details and test cases needed to get 100% coverage for Adrastea | Read the macros document provided by vijay |  | Meeting for the sequence and test case development with Nitin |  | Made changes to disable scoreboard in lykan, new testlist for only anvu_tests, single connectivity test with master and name of slave.
[24 empty] | Filled the kichi AR_MEM_MAP and checklist for llvr |  | arch id sheet was changed and uploaded on sharepoint ,attended meeting for the arch id review for sahi and kichi
[24 empty] | New view was created for incorporating the ahb xactor and check for valid solution to incorporate it without any effect on bus intg environment | Pending | cnoc tic test cases were seen for data mismatch, removed the boot rom from test
[25 empty] | Toggle coverage for BIMC | [7 empty] | Get the info about the toggle coverage from external dependencies and merge them, check for mdp tid 5 th bit toggle |  |  | The sanity test case for dcd related to snoc top were run. |  |  |  | Assertion compilation issue was resolved by changing the file assert_pc_noc_protocol_checker_bind.sv file |  | unaligned transaction from the qsb axi 128 bit master shows pending transaction, the code for bus_intg_scbd_qsb_axi128.sv needs to be changed for supporting the same |  | Mails regarding the access for wifi noc was sent |  | Meeting for wifinoc attended | What should be the values of sideband signals at slave end for APB Master |  | Mclaren NOC Q2 with Amit |  |  | Changed the configuration of master and slave vip for getting coverage of: transaction coverage, state coverage , toggle coverage and protocol checks coverage |  | Filed a ticket related to ‘fatal’ error in lykan
[24 empty] | Sent the vdb database to sachin for merging the coverage . | [15 empty] | Assertion compilation issue was resolved by changing assert_pc_noc_perf_checkers_bind.sv
[24 empty] | Snoc coverage:90%,Pcnoc coverage:93% | Complete the toggle q2_h and pending untoggled signals | pcnoc coverage-95%,snoc coverage-92%,bimc coverage-84.77% with exclusions, the mail regarding the toggle for error response from various slave has been sent, the exclusion regarding the transaction matrix was sent to pavan for review |  | pcnoc coverage-96.12,snoc coverage-92.39,bimc coverage-84.83 with exclusion |  |  |  |  | Add the switch for axi xactor timeout increase, so that environmenet variable for the same is not required to be changed |  |  | Assertion Failure of the sanity test case was seen in dump |  |  |  | Dcd script for pcnoc environmenet generated with master remap option as names are different for the masters in rtl and wrapper |  |  |  | HLVR slides for adrastea noc was read. |  | Extracted coverage points from discovery VIP of APB | Testplan for all the testcases written for coverage, test, corner case scoreboard ( if we need any change) |  |  |  |  | Protocol check coverage was not able to be generated, the issue was reported to sharat shreedhar, -need to get it closed with vip team |  | Made HLVR for Jacala-NOC
[26 empty] | qdss cfg multimaster q3 test failure was seen for hang issue, mail was sent for the same |  | CR filed for the qdss cfg multimaster test, as the reserved part of the slave had ready signal tied to low due to which the test was hang | [7 empty] | The change in the number of qsb axi master was made in the bind file for correcting the checker, the sanity tests were passed |  |  |  | Run Tests were incomplete due to unavailable pre compiled rtl, reported issue for rebase. |  |  |  | Meeting for pcie timeout |  | Ran the gen noc tb for new baseline of lykan after rebasing | VIP integration and sequences : Reading and understanding |  |  |  |  | Published the report of coverage to nitin after facing issue regarding the regression run on san diego server. |  | Updated Bugzilla after issue related to first sequence run got resolved by Deepak
[26 empty] | The address range for tcu slave and bimc cfg was changed for covering toggle coverage part of address, the test of dap is to checked for pid not toggling in coverage(ran test), |  | rebased to kichi_v1.0_p2q1r13_verif_v1.52, and released the baseline for kichi bus integration, merging issues were seen. | [8 empty] | To generate the environment for mnoc dcd top module |  |  | Test case failure of noc was seen with amit. | [5 empty] | The coverage report for mclaren pcnoc dcd was generated for test cases | CSR – Nitin bhatnagar |  |  | Mailed about CSR verification, internal debug slave verification
[27 empty] | llvr slides to be made,get reviewed and upload | [12 empty] | DCD snoc files were checked in and required elements were made.
[27 empty] | complete the check list task before llvr | [12 empty] | Demodifying the component of dcd wrapper caused problem, issue reported to scm.help
[27 empty] | test cases merge for toggle coverage completeness and send all the mails regarding signals not toggling and exclusions need to be reviewed | sent mail for the untoggled signals, have made test for mss nav error response, cats error response, | [8 empty] | To check for multi master multi slave test cases |  |  | Coverage for eldarion bimc got reviewed | [5 empty] | Analyzed the coverage report for mclaren pcnoc dcd the qhm3 coverage was not 100% . | Mail followup for adrastea NOC
[40 empty] | Test case for the q2_h were run for size of ebi_phy_cfg slave, ooo test for lpass master, for eldarion bimc coverage | [5 empty] | Atended the NOC information meeting | Vishal karna to add Deepak too in adrastea noc
Made new stream and view for Anurag to work on NOC lykan

## Daily status
2016-09-01 | ¦ | 2016-09-02 | ¦
1. Tried to fix Date Calender issue | ¦¦¦¦¦¦¦¦¦¦ | 1. Cool Disco app - a.) Fetching Album Info b.) Gallery Creation(not Complete) | ¦¦¦¦¦¦¦¦¦¦
2. Cool Disco app - a.) View Pager Creation b.) Fragment Conversion c.) Tabs Handling | ¦¦¦¦¦¦¦¦¦¦¦¦ |  | ¦¦¦¦¦¦¦¦¦¦¦¦
| ¦¦¦¦¦¦¦¦¦¦ |  | ¦¦¦¦¦¦¦¦¦¦
| ¦¦¦¦¦¦¦¦¦¦ |  | ¦¦¦¦¦¦¦¦¦¦